## Slide 1
01
Ready to reference to ACQF – 2025/26

## Slide 2: Introduction
Purpose: Operationalize NQF-ACQF referencing with Guideline 3 as the anchor.
ACQF’s Role: Referencing is a core function of ACQF as a Meta-framework for the African continent connecting AU national/regional frameworks.
Key Output: Level-to-level correspondence via a referencing report based on
4 criteria : (i) connections of NQFs to ACQF levels/descriptors, (ii) outcomes-based learning, (iii) transparency around NQF qualifications, (iv) alignment to ACQF QA principles
+ governance, procedures and follow-up steps.

## Slide 3: ACQF Network’s Role
Technical Cluster Tasks:
• Steer and support referencing to ACQF & related follow-up steps.
Communicate achievements around ACQF referencing
• Advocate for qualifications recognition.
• Cooperate with Addis Convention Committee and other regional networks
• Track progress (e.g., publication of reports, ACQF level usage, registers, communication and dissemination).

## Slide 4: Starting the Process
Self-assessment: Evaluate readiness (except pilot countries in 2024).
Formal notification to ACQF Network to commence
Secure political commitment (Ministry of Education/Labour mandate).
Designate lead organization (e.g., National Qualifications Authority).
Form National Referencing Committee (NRC) with multi-stakeholder representation.
Develop Terms of Reference (TOR) and deliverables (Inception, Draft, Final Reports).

## Slide 5: National Consultations
Objective: Build consensus, validate findings, ensure legitimacy.
• Stakeholders: Government, educators, QA bodies, employers, learners, NGOs.
• Methods: Workshops, surveys, sector dialogues, public feedback.
• Outcome: Updated report reflecting stakeholder input.

## Slide 6: ACQF II Support (2025–26)
• Peer Learning Activities (PLAs): Cross-country knowledge sharing
• NRC Workshops: In-country technical training.
• Referencing Report Review: Peer/expert feedback.
• Progress Dashboard: Public tracker for country status updates.

## Slide 7: Next Steps & Q&A
• 2025–26 Focus: Strengthen peer learning, finalize referencing reports.
• Call to Action: Engage stakeholders, leverage ACQF II support.
• ACQF Panel assessment: validation followed by publication.
Outcomes : All qualifications/registers bear clear reference to ACQF levels.
Q&A